## Read Me - Updated
ELKITCH & IMPEX — UPDATED PROJECT TRACKER
Basis | Updated using the supplied project timeline markdown (May 2025–October 2026) and the existing workbook.
Historical periods | See 'Updated Source Timeline'. Periods follow the source; uncertain dates remain explicitly marked as unconfirmed.
Future task dates | See 'Task Plan'. These are proposed next-action dates from 2026-10-20 onward, not proof that work was completed.
Priority | Critical = blocking payment/access/validation; High = operational or integration validation; Medium = routine verification/scope confirmation.
Important caution | Sale Mela has insufficient dated task history in the source; its first task is to confirm scope/status. Do not report proposed dates as historical employment records.
Projects included | Impex camera attendance, Impex attendance improvements, Impex Saudi call center automation, Factory Machine Vision, Canteen, Security, Energy, Water, Oil, Driver App, Gate Management, Fleet, Production, Agentic AI Factory, Sale Mela.

## Project Register
Project | Workstream / Scope | Timeline (supported by records) | Key work completed / progress | Latest known status | Pending / dependencies | Status confidence
Elkitch – Agentic AI Factory | Enterprise agentic AI architecture, Azure, Databricks, PostgreSQL, RAG, local LLM, sub-agents, data ingestion, project management | Earlier planning/research; detailed dated updates 2026-09-29 to 2026-10-19 | Compared agentic AI platforms and RAG frameworks; reviewed safe agent operation and eval/context handling; designed cost-optimized Azure architecture; reviewed vendor plans; reduced estimate from $536.89/month to $31.17/month; reviewed and approved revised Azure plan from user's side; collected department data requirements; planned sub-agent workflows and skills; reviewed Databricks cleaning; planned raw/silver/gold data layers; built initial data-ingestion system; checked PostgreSQL ingestion and Azure compatibility; prepared local LLM plan targeting at least 8B parameters; built a custom project-management app for employee tasks and future AI Factory integration. | In progress | Azure account/access and cloud-storage approval; approval to start full development (Nasrudeen Sir/team); implementation/testing and validation of data ingestion and agent workflows. | High for pending dependencies explicitly mentioned; overall status inferred from latest updates
Impex – Saudi Arabia Automation / Call Center | WhatsApp customer support, complaints, dealers, admin dashboard, payment gateway and Saudi service pricing | Historical work; dated updates visible 2026-09-29 to 2026-10-13 | Built WhatsApp customer complaint/support workflow with WhatsApp Business, Meta Business Suite, Interakt and n8n; complaint UID tracking, feedback/rating, status/follow-up pages, Arabic-English translation and language selection; dealer registration/edit/status management; admin complaint and feedback dashboards, exports, filters and image links; worked on Moyasar payment integration and bank payment option; updated payment proof in admin panel; tested payment flow with provided test details after Moyasar approval; adjusted refrigerator service cost to 300 SAR; later returned TV service price to 150 SAR after successful testing with Saudi team; reviewed/structured video input for customer-service automation ad; held a meeting and listed connected banks. | Partially implemented; verification/final confirmation pending | Saudi team verification in admin panel/payment flow; some earlier records also mention CR/payment-gateway verification and complete Saudi-number workflow testing. | High for payment verification pending in updates; broader project status inferred
Impex – Attendance AI Camera | Face-recognition attendance, staff records, punch data, server and monitoring | Historical setup; detailed updates 2026-10-09 and 2026-10-12 | Configured new attendance server and migrated data; tested check-in/out from 5 to 20+ and 200+ employees; improved recognition speed from about 3 seconds to 1.5 seconds; added Google Sheets/Excel integration, custom staff upload, machine ID vs camera punch comparison, session graphs, alerts and device ping monitoring; updated staff list by adding new staff and removing former staff; added September punch data for checking; earlier records note machine attendance data through 15 August. | Operational with ongoing data checks and maintenance | Final testing/deployment and monitoring items were noted in the historical summary; current production status not explicitly confirmed. | Medium; latest staff/punch updates are explicit, final overall deployment state is not
Elkitch – Fleet Dashboard | Live vehicle tracking, Millitrack API and map | Historical dashboard work; detailed update 2026-09-30 | Replaced demo data with live Millitrack GPS data; improved map and circle/geofence-style visualization; added new vehicle API; updated server to fetch required vehicle data; added vehicle to map. | Partially implemented / integration updates made | Vehicle names need correction after the API's vehicle-name data is updated. | High for pending name correction
Elkitch – Production Dashboard / Smart Factory | PMS production data, machine counts, paint booth, press shop, Robo Line laser engraving and sandblasting | Historical dashboard work; detailed updates 2026-10-14 to 2026-10-16 | Integrated rejection/rework values through PMS API; tested MQTT object counting; added machines and No Production tables; updated Paint Booth and Press Shop displays; inspected sandblasting machine and proposed product-count collection solution; enabled Ethernet connectivity for Robo Line laser engraving machine; tested file-watcher approach to count engraved parts. | In progress | Change watcher/machine interface language from Chinese to English; validate watcher-based counting in production. Ethernet connectivity was enabled. | High for explicitly stated next steps
Elkitch – Sale Mela Application | Employee data-entry web app, Excel export and image capture | Detailed updates 2026-10-14 to 2026-10-15 | Created a Sale Mela web app with data-entry form, Excel export, image upload/storage and usability improvements; added camera-based auto-fill to make data entry faster and clearer; improved prefilled data. | Core features reported as implemented | No explicit outstanding blocker recorded; formal user acceptance/deployment status not stated. | Medium
Elkitch – Canteen Dashboard | Coupon printing, gift coupons, expenses, item lists, reports and device sync | Historical ongoing improvements; dated updates 2026-10-05 and 2026-10-16 | Built coupon printing with USB/tablet/mobile support; manual/scanned count separation; Bluetooth-aware meal buttons; SQLite refresh fixes; Tailscale reconnection; protected settings and list management; expense tracking and Excel comparisons; added missing coupon records for 2026-09-30; added Dasara gift coupon page and custom validity-date option. | Ongoing enhancements; latest requested features added | No explicit blocker in latest update; routine validation/printing checks may still be required but were not explicitly stated. | Medium
Elkitch – Energy Dashboard | Machine energy monitoring and cost/consumption analysis | Historical work; exact start/end dates not stated | Integrated MQTT machine consumption; added date-wise consumption differences, backend income/cost flow, global time-range picker and energy/solar analysis visualizations. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Water Dashboard | Water tank and plant consumption monitoring | Historical work; exact start/end dates not stated | Added tank-level animation and MQTT monitoring for fire pump, Plants 1–3 and canteen; added total consumption display, with a recorded test value such as 16.3 kL. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Oil Dashboard | Oil consumption monitoring | Historical work; exact start/end dates not stated | Integrated MQTT-based oil-consumption values and total oil consumption monitoring. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Security Dashboard | Checkpoints, MQTT alarms and warehouse monitoring | Historical work; exact start/end dates not stated | Reordered checkpoints 1–5; integrated MQTT; added alarm toggle and temporary disable for checkpoint 5 during network issues; configured day-shift timer and 10-minute warehouse alarm intervals. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Driver App | Driver, trip and fuel records | Historical work; exact start/end dates not stated | Built web app with Google Drive/Sheets; added trip KM, mileage, fuel type, fuel volume and amount; added driver filters/manual sync; connected vehicle fuel data with Gate Management. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Gate Management / Gate App | Gate entry logs, vehicles and integration | Historical work; exact start/end dates not stated | Integrated gate entry logs with canteen dashboard; linked vehicle information with Driver App; synchronized fuel data; worked on timezone and checkout-log handling. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Factory Machine Vision / Vision Assembly | Machine vision tools and production-line calibration | Historical work; 2025 dates are partially supported by resume/context; exact project range not fully stated | Worked on SLAW/SLAM, CG/BG, BFA/CFA, Luster, B01, BFA-1 A Side and BFA-2 B Side; used Vision Assembly, LBAS Capture and Vision Code; learned geometry, line/circle, line-to-line and intersection tools; worked with FOV/calibration and 40x/50x input units; solved Xover line/intersection issue using edge polarity; reviewed image retention and backup. | Historical work; completion status not tracked | No current status or blocker recorded. | Low

## Dated Work Updates
Date | Project | Work update | Work category | Status / notes
2026-09-29 | Elkitch – Agentic AI Factory | Compared agentic AI platforms and frameworks; focused on safe operation in Azure/Databricks/storage and avoiding context issues affecting evals. | Research/design | No completion claim
2026-09-30 | Elkitch – Agentic AI Factory | Requested/recommended a reduced Azure plan using only required Storage, Databricks and PostgreSQL services; developed a least-cost architecture. | Architecture/cost optimization | Plan revised; approval/process dependent
2026-09-30 | Elkitch – Fleet Dashboard | Added new vehicle API; updated server fetching for required data; added vehicle to map. | Integration | Vehicle-name corrections pending updated API data
2026-10-01 | Elkitch – Agentic AI Factory | Reviewed vendor plan and reduced estimate from $536.89/month to $31.17/month. | Cost optimization | Revised plan prepared
2026-10-05 | Elkitch – Agentic AI Factory | Reviewed revised Azure account plan and approved it from user's side to proceed. | Plan review | Team/account approval and access still need to be tracked separately
2026-10-05 | Elkitch – Canteen Dashboard | Added missing coupon records requested by Sinan Sir for 2026-09-30. | Data correction | Reported as completed
2026-10-06 | Elkitch – Agentic AI Factory | Reviewed RAG frameworks and local-agent skill creation; reviewed Databricks data cleaning; Azure access approval pending. | Research/data preparation | Waiting for access approval
2026-10-08 | Elkitch – Agentic AI Factory | Reviewed data collection and listed required datasets; waiting for Nasrudeen Sir's approval for setup and agent development. | Requirements | Approval pending
2026-10-08 | Elkitch – Agentic AI Factory | Prepared initial local LLM requirements plan targeting at least 8B parameters for capable agents. | Local LLM planning | Requirements plan, not a deployed model
2026-10-09 | Impex – Attendance AI Camera | Added new staff and removed former staff; added September punch data for checking. | Data maintenance/testing | Punch data added for validation
2026-10-09 | Elkitch – Agentic AI Factory | Requested Azure/cloud storage access; checked node for ingesting data into PostgreSQL. | Integration preparation | Access approval pending
2026-10-12 | Elkitch – Agentic AI Factory | Listed possible sub-agents and their task/skill workflows; prepared next-month cloud plan pending Azure approval. | Agent design/planning | Implementation depends on access
2026-10-13 | Elkitch – Agentic AI Factory | Explored alternative data connection path while Azure approval was pending; built initial ingestion flow and grouped data into raw, silver and gold layers. | Prototype/data engineering | Alternative path explored; production status not confirmed
2026-10-14 | Elkitch – Agentic AI Factory | Checked new Azure server and PostgreSQL data compatibility. | Compatibility check | Full integration status not confirmed
2026-10-14 | Elkitch – Production Dashboard | Checked sandblasting machine requirements for product counting and proposed a solution. | Machine integration analysis | Implementation status not stated
2026-10-14 | Elkitch – Sale Mela Application | Built web app with data-entry form, Excel export, image support and employee usability improvements. | Application development | Core features reported built
2026-10-15 | Elkitch – Sale Mela Application | Added camera-based auto-fill and improved prefilled data. | Feature enhancement | Reported as added
2026-10-15 | Elkitch – Production Dashboard | Checked Robo Line laser engraver; explored file watcher to count engraved parts; Ethernet was required. | Machine integration | Ethernet required at this point
2026-10-16 | Elkitch – Production Dashboard | Enabled Ethernet; tested watcher; noted machine language needs changing from Chinese to English. | Machine integration | Language change remains a dependency
2026-10-16 | Elkitch – Canteen Dashboard | Added Dasara gift coupon page with printing and custom validity-date option. | Feature enhancement | Reported as added
2026-10-19 | Elkitch – Agentic AI Factory | Built custom project-management app for employee task management and workflow; planned later integration with Agentic AI Factory for department efficiency. | Internal application/prototype | Future AI Factory integration planned

## Key Task Summary
Workstream | Project | Summary | Date / period | Completion / dependency note
Architecture and cost | Agentic AI Factory | Vendor plan reviewed and cost reduced from $536.89/month to $31.17/month. | 2026-10-01 | Revised plan; actual billing/production deployment not confirmed.
Cloud access | Agentic AI Factory | Azure/cloud storage access and approval requested; approval from Nasrudeen Sir/team was pending in updates. | 2026-10-06 to 2026-10-09 | Explicit blocker.
Data architecture | Agentic AI Factory | Databricks cleaning reviewed; initial ingestion and raw/silver/gold data layers created; PostgreSQL compatibility/node checked. | 2026-10-06 to 2026-10-14 | Prototype/initial implementation; production readiness not confirmed.
Agent design | Agentic AI Factory | RAG frameworks, local skills, sub-agent workflows and local LLM requirements reviewed; 8B+ parameter target noted. | 2026-10-06 to 2026-10-12 | Planning/research; deployment not confirmed.
Project management | Agentic AI Factory | Custom employee task-management app built; planned future integration with AI Factory. | 2026-10-19 | App reported built; AI Factory integration future work.
Attendance records | Impex Attendance AI Camera | Staff list cleaned and September punch data added for checking. | 2026-10-09 to 2026-10-12 | Data validation/checking purpose.

## Updated Source Timeline
Project | Supported period | Historical work / updates from timeline | Date accuracy / notes
Impex – Camera Attendance System / Machine Comparison | Dec 2025 – Jan 2026 | Developed/tested AI camera attendance; installed on factory ground floor; compared camera punches with machine records; improved identification; added tracker IDs for unidentified entries; tested check-in/out; cleaned employee records. | Month-level period supported by source; exact task dates not confirmed.
Impex – Attendance System Improvements | Jan – Jul 2026; task dates vary | Configured attendance hardware/software; improved recognition from ~3 seconds to ~1.5 seconds; tested with 200+ employees; integrated Excel and Google Sheets; added custom employee uploads; improved image processing; worked on anti-spoofing, validation, browser startup/recovery, n8n device-ping alerts and camera-vs-machine discrepancy investigation. | Month-level period supported by source; exact dates vary.
Impex – Saudi Arabia Call Center Automation | May – Oct 2026 | Researched WhatsApp Business automation with n8n and Interakt; worked on Meta/business verification and documentation; connected Meta webhooks with n8n; developed complaint/customer communication flows; explored AI voice agent; added dealer registration/edit/delete/status; complaint and feedback dashboards; Arabic-English translation; Moyasar payments and alternative bank payment; updated landing-page policies and CR Activity 331233 verification. | Source says exact project start/end dates are not fully confirmed.
Elkitch – Factory Machine Vision | May 2025 onward | Worked across production lines using Vision Assembly, LBAS Capture and Vision Code; practised geometry, line/circle finding, line-to-line and intersection tools; calibration/FOV/edge polarity; investigated line-drawing/intersection issues; supported image storage, backup and troubleshooting. | Exact end date not confirmed.
Elkitch – Canteen Dashboard | Jan 2026 onward | Server migration and bug fixes; Bluetooth-enabled Android workflow; coupon/barcode operations; queue-based printing; USB/Bluetooth and tablet workflows; manual coupon entry; scanned/manual counts; reports and Excel export; item/category/price/quantity management; mobile sync; expense tracking and purchase-rate comparisons; refresh, meal-button and printer handling. | Later task dates and project end date not fully confirmed.
Elkitch – Security Dashboard | Jan – Jun 2026 | Real-time updates and animations; MQTT monitoring and alarm controls; checkpoint and patrol monitoring; checkpoint enable/disable; day-shift timers and warehouse alarms; patrol-alarm loop fixes; success/failure tracking; checkpoint timing and network handling. | Individual task dates vary.
Elkitch – Energy Dashboard | May – Jun 2026 onward | MQTT machine energy data; date-wise consumption differences; backend consumption/cost calculations; global time range; investigated values dropping after server restarts and worked on automatic recovery. | Exact end date not confirmed.
Elkitch – Water Dashboard | May – Jun 2026 onward | MQTT water-level monitoring; tank animations; fire pump, plant areas and canteen monitoring; consumption summaries and total calculations; investigated post-restart data issues and recovery. | Exact end date not confirmed.
Elkitch – Oil Dashboard | May – Jun 2026 onward | MQTT oil-consumption values; display totals, graphs and calculations; investigated resets after server restarts; coordinated values with related factory monitoring. | Exact end date not confirmed.
Elkitch – Driver Application | Apr – May 2026 onward | Google Drive/Sheets integration; trip kilometres and mileage; fuel type; driver filter; fuel volume and amount; manual sync; connected driver/vehicle records with gate-management workflows. | Exact start and end dates not fully confirmed.
Elkitch – Gate Management System | Apr – May 2026 onward | Integrated gate-entry logs with factory dashboards; connected vehicle and driver information with Driver App; fuel information and synchronization; improved gate-entry record flow. | Exact dates not fully confirmed.
Elkitch – Fleet Dashboard | Feb – Mar 2026 | Integrated live Millitrack GPS, replaced demo data, connected frontend/backend, developed trip records and database integration, forward/backward/total distance, daily export, activity logs, movement/halt duration, location details and map-circle visualization. | Period explicitly supported by source.
Elkitch – Production Dashboard | Jan – Oct 2026 | PMS rejection/rework API integration; MQTT object counts; hosting/port-forwarding and machine-line information; added machine/panel rotation progress; automatic 10-second panel rotation; moved machine displays to main dashboard; worked on No Production table and Paint Booth/Press Shop TV displays. | Exact start date not confirmed; later updates Sep–Oct 2026.
Elkitch – Agentic AI Factory | Sep – Oct 2026 | Researched Azure/Databricks architecture; tested Azure AI Foundry; reviewed access, pricing and deployment; consulted vendor/architecture resources; designed potential Databricks pipeline and factory-agent architecture; explored procurement automation and PO tracking for overdue orders, PO checks, delivery delays and supplier checks; considered Google Sheets, Telegram and enterprise integrations; planned Chamraj pilot with possible expansion. | Based on recent updates; cloud access/approval and pilot execution must be verified.
Elkitch – Sale Mela | Dates not confirmed | Project appears in the wider project list; source timeline does not provide sufficient dated tasks to assign reliable dates. | Do not treat a proposed task date as historical completion.

## Task Plan
NOTE: Dates are proposed next-action dates from 2026-10-20 onward, not historical completion dates. Historical periods are in 'Updated Source Timeline'.
Planned Date | Project | Workstream | Next Task | Expected Output | Priority | Dependency / Notes | Date Type
2026-10-20 | Elkitch – Agentic AI Factory | Cloud access & approvals | Confirm Azure account, cloud storage access and required approvals with the responsible team. | Access confirmed or a documented blocker/owner/date recorded. | Critical | Historical notes indicate approval/access was pending; verify current status before proceeding. | Proposed next action
2026-10-21 | Elkitch – Agentic AI Factory | Architecture & cost | Revalidate the reduced Azure/Databricks/PostgreSQL architecture and actual billing estimates. | Approved architecture and cost baseline. | High | Previous estimate was reduced from $536.89/month to $31.17/month; confirm current pricing and scope. | Proposed next action
2026-10-22 | Elkitch – Agentic AI Factory | Data pipeline | Validate Raw/Silver/Gold ingestion flow and PostgreSQL compatibility using a representative dataset. | Documented successful ingestion and data-quality checks. | High | Requires access to the relevant environment and data. | Proposed next action
2026-10-23 | Elkitch – Agentic AI Factory | Procurement agent pilot | Define test cases for overdue POs, PO validation, delivery delays and supplier checks; select the Chamraj pilot dataset. | Pilot scope, test dataset and acceptance criteria. | High | Confirm data permissions and integrations (e.g., Sheets/Telegram/enterprise systems). | Proposed next action
2026-10-26 | Impex – Saudi Arabia Call Center Automation | Payment verification | Run a controlled Moyasar payment test and verify transaction, receipt and admin-panel records with the Saudi team. | Payment flow verified and issues logged/resolved. | Critical | Saudi-team verification and valid test credentials/payment setup required. | Proposed next action
2026-10-27 | Impex – Saudi Arabia Call Center Automation | Business verification | Check Meta/business documentation requirements, including CR Activity 331233, and record the current verification status. | Checklist of accepted/pending documents and next owner action. | High | External platform/business documentation dependency. | Proposed next action
2026-10-28 | Impex – Saudi Arabia Call Center Automation | WhatsApp automation | Test complaint intake, dealer status flow, Arabic-English translation and customer feedback dashboard end-to-end. | Test results and prioritized fixes. | High | Depends on working WhatsApp/Meta integrations and business verification as applicable. | Proposed next action
2026-10-29 | Impex – Attendance System | Attendance data validation | Validate September punch records, employee roster changes and camera-versus-machine discrepancies. | Reconciled exception list and corrected records where authorized. | High | Confirm source data and authorized corrections. | Proposed next action
2026-10-30 | Impex – Attendance System | Reliability & alerts | Re-test recognition performance, anti-spoofing checks, startup/recovery and n8n device-ping alerts. | Test log with timings, failure cases and recovery results. | Medium | Use approved test conditions; recognition target previously reported around 1.5 seconds. | Proposed next action
2026-11-02 | Elkitch – Production Dashboard | Panel rotation & production views | Verify 10-second panel rotation, machine/panel progress indicators, No Production table and TV display changes. | Validated display checklist and issue list. | High | Confirm with production users and actual machine data. | Proposed next action
2026-11-03 | Elkitch – Production Dashboard | Machine counting | Validate sandblasting product count and Robo Line laser-engraving file-watcher counts against physical output. | Count comparison results and documented machine-language/interface dependency. | High | Source history notes machine/interface language change to English as a potential dependency; verify current state. | Proposed next action
2026-11-04 | Elkitch – Fleet Dashboard | Live vehicle API | Verify new vehicle API data and correct vehicle names only after the API source is corrected. | Map and vehicle-name list reconciled with API data. | High | API data/name mismatch must be resolved before final naming corrections. | Proposed next action
2026-11-05 | Elkitch – Canteen Dashboard | Printing & synchronization | Test USB/Bluetooth printing, tablet/mobile sync, manual/scanned coupon counts and queue-based printing. | End-to-end canteen test results and defect list. | High | Confirm printer/device availability and production environment. | Proposed next action
2026-11-06 | Elkitch – Security Dashboard | MQTT & alarm reliability | Test checkpoint enable/disable, patrol success/failure, interval timers, warehouse alarms and network recovery. | Alarm and patrol validation report. | High | Coordinate a safe test window with security operations. | Proposed next action
2026-11-09 | Elkitch – Energy Dashboard | Consumption and recovery | Compare MQTT consumption readings with source values; test date-range calculations and recovery after service restart. | Reconciled energy values and restart/recovery test record. | High | Requires source meter values and controlled restart window. | Proposed next action
2026-11-10 | Elkitch – Water Dashboard | Water readings and recovery | Validate tank-level animation, fire-pump/plant/canteen values and total-consumption calculations after restart. | Verified water dashboard values and recovery checklist. | High | Compare with trusted source readings; do not assume prior sample total remains current. | Proposed next action
2026-11-11 | Elkitch – Oil Dashboard | Oil readings and recovery | Verify MQTT values, totals, graphs and persistence after restart against source readings. | Verified oil totals and documented recovery behavior. | Medium | Requires source readings and controlled restart window. | Proposed next action
2026-11-12 | Elkitch – Driver Application | Driver/fuel records | Verify trip KM, mileage, fuel type/volume/amount, driver filter and manual sync with Google Sheets/Drive. | Validated sample records and sync result. | High | Requires current sheet permissions and test vehicle records. | Proposed next action
2026-11-13 | Elkitch – Gate Management System | Gate/driver integration | Test gate-entry logs and vehicle/driver synchronization with the Driver App and related dashboards. | End-to-end gate record and synchronization check. | High | Coordinate a test entry and confirm time/date handling. | Proposed next action
2026-11-16 | Elkitch – Factory Machine Vision | Vision tools & calibration | Check calibration, field of view, line/circle/intersection tools and edge-polarity-dependent cases on selected line samples. | Machine-wise validation log and unresolved issue list. | Medium | Requires machine access and approved sample parts. | Proposed next action
2026-11-17 | Elkitch – Factory Machine Vision | Image retention & backup | Verify image retention settings, backup completeness and restoration/readability for sampled images. | Retention/backup evidence and any corrective actions. | Medium | Confirm current retention policy with factory/IT. | Proposed next action
2026-11-18 | Elkitch – Sale Mela | Scope confirmation | Confirm current feature list, latest build, outstanding issues, owner and deployment status before assigning implementation tasks. | Confirmed scope and actionable backlog with real dates. | Medium | Historical source does not contain enough dated task detail to infer completion or deployment status. | Proposed next action