## Project Register
Project | Workstream / Scope | Timeline (supported by records) | Key work completed / progress | Latest known status | Pending / dependencies | Status confidence
Elkitch – Agentic AI Factory | Enterprise agentic AI architecture, Azure, Databricks, PostgreSQL, RAG, local LLM, sub-agents, data ingestion, project management | Earlier planning/research; detailed dated updates 2026-09-29 to 2026-10-19 | Compared agentic AI platforms and RAG frameworks; reviewed safe agent operation and eval/context handling; designed cost-optimized Azure architecture; reviewed vendor plans; reduced estimate from $536.89/month to $31.17/month; reviewed and approved revised Azure plan from user's side; collected department data requirements; planned sub-agent workflows and skills; reviewed Databricks cleaning; planned raw/silver/gold data layers; built initial data-ingestion system; checked PostgreSQL ingestion and Azure compatibility; prepared local LLM plan targeting at least 8B parameters; built a custom project-management app for employee tasks and future AI Factory integration. | In progress | Azure account/access and cloud-storage approval; approval to start full development (Nasrudeen Sir/team); implementation/testing and validation of data ingestion and agent workflows. | High for pending dependencies explicitly mentioned; overall status inferred from latest updates
Impex – Saudi Arabia Automation / Call Center | WhatsApp customer support, complaints, dealers, admin dashboard, payment gateway and Saudi service pricing | Historical work; dated updates visible 2026-09-29 to 2026-10-13 | Built WhatsApp customer complaint/support workflow with WhatsApp Business, Meta Business Suite, Interakt and n8n; complaint UID tracking, feedback/rating, status/follow-up pages, Arabic-English translation and language selection; dealer registration/edit/status management; admin complaint and feedback dashboards, exports, filters and image links; worked on Moyasar payment integration and bank payment option; updated payment proof in admin panel; tested payment flow with provided test details after Moyasar approval; adjusted refrigerator service cost to 300 SAR; later returned TV service price to 150 SAR after successful testing with Saudi team; reviewed/structured video input for customer-service automation ad; held a meeting and listed connected banks. | Partially implemented; verification/final confirmation pending | Saudi team verification in admin panel/payment flow; some earlier records also mention CR/payment-gateway verification and complete Saudi-number workflow testing. | High for payment verification pending in updates; broader project status inferred
Impex – Attendance AI Camera | Face-recognition attendance, staff records, punch data, server and monitoring | Historical setup; detailed updates 2026-10-09 and 2026-10-12 | Configured new attendance server and migrated data; tested check-in/out from 5 to 20+ and 200+ employees; improved recognition speed from about 3 seconds to 1.5 seconds; added Google Sheets/Excel integration, custom staff upload, machine ID vs camera punch comparison, session graphs, alerts and device ping monitoring; updated staff list by adding new staff and removing former staff; added September punch data for checking; earlier records note machine attendance data through 15 August. | Operational with ongoing data checks and maintenance | Final testing/deployment and monitoring items were noted in the historical summary; current production status not explicitly confirmed. | Medium; latest staff/punch updates are explicit, final overall deployment state is not
Elkitch – Fleet Dashboard | Live vehicle tracking, Millitrack API and map | Historical dashboard work; detailed update 2026-09-30 | Replaced demo data with live Millitrack GPS data; improved map and circle/geofence-style visualization; added new vehicle API; updated server to fetch required vehicle data; added vehicle to map. | Partially implemented / integration updates made | Vehicle names need correction after the API's vehicle-name data is updated. | High for pending name correction
Elkitch – Production Dashboard / Smart Factory | PMS production data, machine counts, paint booth, press shop, Robo Line laser engraving and sandblasting | Historical dashboard work; detailed updates 2026-10-14 to 2026-10-16 | Integrated rejection/rework values through PMS API; tested MQTT object counting; added machines and No Production tables; updated Paint Booth and Press Shop displays; inspected sandblasting machine and proposed product-count collection solution; enabled Ethernet connectivity for Robo Line laser engraving machine; tested file-watcher approach to count engraved parts. | In progress | Change watcher/machine interface language from Chinese to English; validate watcher-based counting in production. Ethernet connectivity was enabled. | High for explicitly stated next steps
Elkitch – Sale Mela Application | Employee data-entry web app, Excel export and image capture | Detailed updates 2026-10-14 to 2026-10-15 | Created a Sale Mela web app with data-entry form, Excel export, image upload/storage and usability improvements; added camera-based auto-fill to make data entry faster and clearer; improved prefilled data. | Core features reported as implemented | No explicit outstanding blocker recorded; formal user acceptance/deployment status not stated. | Medium
Elkitch – Canteen Dashboard | Coupon printing, gift coupons, expenses, item lists, reports and device sync | Historical ongoing improvements; dated updates 2026-10-05 and 2026-10-16 | Built coupon printing with USB/tablet/mobile support; manual/scanned count separation; Bluetooth-aware meal buttons; SQLite refresh fixes; Tailscale reconnection; protected settings and list management; expense tracking and Excel comparisons; added missing coupon records for 2026-09-30; added Dasara gift coupon page and custom validity-date option. | Ongoing enhancements; latest requested features added | No explicit blocker in latest update; routine validation/printing checks may still be required but were not explicitly stated. | Medium
Elkitch – Energy Dashboard | Machine energy monitoring and cost/consumption analysis | Historical work; exact start/end dates not stated | Integrated MQTT machine consumption; added date-wise consumption differences, backend income/cost flow, global time-range picker and energy/solar analysis visualizations. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Water Dashboard | Water tank and plant consumption monitoring | Historical work; exact start/end dates not stated | Added tank-level animation and MQTT monitoring for fire pump, Plants 1–3 and canteen; added total consumption display, with a recorded test value such as 16.3 kL. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Oil Dashboard | Oil consumption monitoring | Historical work; exact start/end dates not stated | Integrated MQTT-based oil-consumption values and total oil consumption monitoring. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Security Dashboard | Checkpoints, MQTT alarms and warehouse monitoring | Historical work; exact start/end dates not stated | Reordered checkpoints 1–5; integrated MQTT; added alarm toggle and temporary disable for checkpoint 5 during network issues; configured day-shift timer and 10-minute warehouse alarm intervals. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Driver App | Driver, trip and fuel records | Historical work; exact start/end dates not stated | Built web app with Google Drive/Sheets; added trip KM, mileage, fuel type, fuel volume and amount; added driver filters/manual sync; connected vehicle fuel data with Gate Management. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium
Elkitch – Gate Management / Gate App | Gate entry logs, vehicles and integration | Historical work; exact start/end dates not stated | Integrated gate entry logs with canteen dashboard; linked vehicle information with Driver App; synchronized fuel data; worked on timezone and checkout-log handling. | Previously implemented; current completion not confirmed | No explicit current blocker recorded. | Low to medium

## Dated Work Updates
Date | Project | Work update | Work category | Status / notes
2026-09-29 | Elkitch – Agentic AI Factory | Compared agentic AI platforms and frameworks; focused on safe operation in Azure/Databricks/storage and avoiding context issues affecting evals. | Research/design | No completion claim
2026-09-30 | Elkitch – Agentic AI Factory | Requested/recommended a reduced Azure plan using only required Storage, Databricks and PostgreSQL services; developed a least-cost architecture. | Architecture/cost optimization | Plan revised; approval/process dependent
2026-09-30 | Elkitch – Fleet Dashboard | Added new vehicle API; updated server fetching for required data; added vehicle to map. | Integration | Vehicle-name corrections pending updated API data
2026-10-01 | Elkitch – Agentic AI Factory | Reviewed vendor plan and reduced estimate from $536.89/month to $31.17/month. | Cost optimization | Revised plan prepared
2026-10-05 | Elkitch – Agentic AI Factory | Reviewed revised Azure account plan and approved it from user's side to proceed. | Plan review | Team/account approval and access still need to be tracked separately
2026-10-05 | Elkitch – Canteen Dashboard | Added missing coupon records requested by Sinan Sir for 2026-09-30. | Data correction | Reported as completed
2026-10-06 | Elkitch – Agentic AI Factory | Reviewed RAG frameworks and local-agent skill creation; reviewed Databricks data cleaning; Azure access approval pending. | Research/data preparation | Waiting for access approval
2026-10-08 | Elkitch – Agentic AI Factory | Reviewed data collection and listed required datasets; waiting for Nasrudeen Sir's approval for setup and agent development. | Requirements | Approval pending
2026-10-08 | Elkitch – Agentic AI Factory | Prepared initial local LLM requirements plan targeting at least 8B parameters for capable agents. | Local LLM planning | Requirements plan, not a deployed model
2026-10-09 | Impex – Attendance AI Camera | Added new staff and removed former staff; added September punch data for checking. | Data maintenance/testing | Punch data added for validation
2026-10-09 | Elkitch – Agentic AI Factory | Requested Azure/cloud storage access; checked node for ingesting data into PostgreSQL. | Integration preparation | Access approval pending
2026-10-12 | Elkitch – Agentic AI Factory | Listed possible sub-agents and their task/skill workflows; prepared next-month cloud plan pending Azure approval. | Agent design/planning | Implementation depends on access
2026-10-13 | Elkitch – Agentic AI Factory | Explored alternative data connection path while Azure approval was pending; built initial ingestion flow and grouped data into raw, silver and gold layers. | Prototype/data engineering | Alternative path explored; production status not confirmed
2026-10-14 | Elkitch – Agentic AI Factory | Checked new Azure server and PostgreSQL data compatibility. | Compatibility check | Full integration status not confirmed
2026-10-14 | Elkitch – Production Dashboard | Checked sandblasting machine requirements for product counting and proposed a solution. | Machine integration analysis | Implementation status not stated
2026-10-14 | Elkitch – Sale Mela Application | Built web app with data-entry form, Excel export, image support and employee usability improvements. | Application development | Core features reported built
2026-10-15 | Elkitch – Sale Mela Application | Added camera-based auto-fill and improved prefilled data. | Feature enhancement | Reported as added
2026-10-15 | Elkitch – Production Dashboard | Checked Robo Line laser engraver; explored file watcher to count engraved parts; Ethernet was required. | Machine integration | Ethernet required at this point
2026-10-16 | Elkitch – Production Dashboard | Enabled Ethernet; tested watcher; noted machine language needs changing from Chinese to English. | Machine integration | Language change remains a dependency
2026-10-16 | Elkitch – Canteen Dashboard | Added Dasara gift coupon page with printing and custom validity-date option. | Feature enhancement | Reported as added
2026-10-19 | Elkitch – Agentic AI Factory | Built custom project-management app for employee task management and workflow; planned later integration with Agentic AI Factory for department efficiency. | Internal application/prototype | Future AI Factory integration planned

## Key Task Summary
Workstream | Project | Summary | Date / period | Completion / dependency note
Architecture and cost | Agentic AI Factory | Vendor plan reviewed and cost reduced from $536.89/month to $31.17/month. | 2026-10-01 | Revised plan; actual billing/production deployment not confirmed.
Cloud access | Agentic AI Factory | Azure/cloud storage access and approval requested; approval from Nasrudeen Sir/team was pending in updates. | 2026-10-06 to 2026-10-09 | Explicit blocker.
Data architecture | Agentic AI Factory | Databricks cleaning reviewed; initial ingestion and raw/silver/gold data layers created; PostgreSQL compatibility/node checked. | 2026-10-06 to 2026-10-14 | Prototype/initial implementation; production readiness not confirmed.
Agent design | Agentic AI Factory | RAG frameworks, local skills, sub-agent workflows and local LLM requirements reviewed; 8B+ parameter target noted. | 2026-10-06 to 2026-10-12 | Planning/research; deployment not confirmed.
Project management | Agentic AI Factory | Custom employee task-management app built; planned future integration with AI Factory. | 2026-10-19 | App reported built; AI Factory integration future work.
Attendance records | Impex Attendance AI Camera | Staff list cleaned and September punch data added for checking. | 2026-10-09 to 2026-10-12 | Data validation/checking purpose.

## Task Plan
Note: Dates below are proposed next-action dates created from the latest known status as of 2026-10-20; they are not claims that the tasks were completed on those dates.
Planned Date | Project / Workstream | Next Task | Expected Output / Acceptance Check | Priority | Dependency / Notes | Date Type
2026-10-20 | Elkitch – Agentic AI Factory | Follow up on Azure account, cloud storage access and approval with Nasrudeen Sir/team. | Written access/approval status and confirmed owner for next step. | Critical | Development is blocked until access and approval are confirmed. | Proposed next action
2026-10-21 | Elkitch – Agentic AI Factory | Validate the initial ingestion pipeline and Raw/Silver/Gold data-layer flow using available sample data. | Documented successful run, data-quality checks and errors. | High | Use currently available access; production readiness not yet confirmed. | Proposed next action
2026-10-22 | Elkitch – Agentic AI Factory | Test PostgreSQL ingestion/node and verify Azure data compatibility. | Test results for schema, connectivity, inserts and failures. | High | Requires the relevant server/database credentials. | Proposed next action
2026-10-23 | Elkitch – Agentic AI Factory | Convert sub-agent workflows into a first pilot scope and evaluation checklist. | One department pilot scope, tools/permissions, success metrics and human approval points. | High | Build on existing RAG/local skill research; do not claim deployment before testing. | Proposed next action
2026-10-26 | Impex – Saudi Arabia Automation / Call Center | Run an end-to-end Moyasar payment test and confirm payment proof/status in the admin panel with Saudi team. | Successful test record and written Saudi team confirmation or issue list. | Critical | Saudi team verification is pending; use approved test details only. | Proposed next action
2026-10-27 | Impex – Saudi Arabia Automation / Call Center | Confirm current service pricing and connected-bank list with the Saudi team. | Approved pricing record: refrigerator service 300 SAR and TV service 150 SAR, unless team confirms a change; bank list validated. | High | Confirm values with team before production use. | Proposed next action
2026-10-28 | Impex – Attendance AI Camera | Validate September punch data against the staff list and source attendance records. | Mismatch report and corrected records approved by the responsible team. | High | Latest update says data was added for checking; validation remains. | Proposed next action
2026-10-29 | Impex – Attendance AI Camera | Run a live check-in/check-out and recognition-speed test; verify monitoring and Google Sheets/Excel sync. | Test log for recognition time, punch accuracy, sync and alerts. | High | Historical speed was about 1.5 seconds; re-measure rather than assume unchanged. | Proposed next action
2026-10-30 | Elkitch – Fleet Dashboard | Follow up for corrected vehicle names in the API and reconcile names with map entries. | Vehicle-name mismatch list resolved or sent to API owner. | High | Depends on API source data being updated. | Proposed next action
2026-11-02 | Elkitch – Production Dashboard / Smart Factory | Change Robo Line laser-engraving machine/interface language to English and retest file watcher. | English interface confirmed; watcher count compared with actual engraved parts. | High | Language change and on-machine validation are outstanding. | Proposed next action
2026-11-03 | Elkitch – Sale Mela Application | Run user acceptance testing for data entry, camera auto-fill, image upload and Excel export. | Issue list and sign-off; record deployment status separately. | Medium | Core features were reported built; deployment/final acceptance is unconfirmed. | Proposed next action
2026-11-04 | Elkitch – Canteen Dashboard | Verify 30/09/2026 coupon records and test Dasara gift coupon printing with custom validity dates. | Printed test coupon and validated records; confirm any missing entries. | Medium | Check printer/device connectivity in the factory environment. | Proposed next action
2026-11-05 | Elkitch – Energy Dashboard | Validate MQTT machine-consumption values, date-range filtering and backend totals against source readings. | Reconciliation sheet for sample machines and date ranges. | Medium | Use current source readings; historical integration does not prove current accuracy. | Proposed next action
2026-11-06 | Elkitch – Water Dashboard | Verify tank-level animation and MQTT readings for firepump, Plants 1–3 and canteen. | Live readings compared with physical/source values; record consumption units. | Medium | Historical example was 16.3 kL; treat as old sample, not current value. | Proposed next action
2026-11-09 | Elkitch – Oil Dashboard | Check MQTT oil-consumption updates and validate total-consumption calculation. | Sample-by-sample reconciliation and logged exceptions. | Medium | Requires access to live machine/topic data. | Proposed next action
2026-11-10 | Elkitch – Security Dashboard | Test checkpoint order/status, alarm toggle, checkpoint 5 network recovery and 10-minute warehouse alarm. | Checklist showing alarm triggers, disable/re-enable behavior and timer accuracy. | High | Ensure testing is coordinated to avoid unintended live alarms. | Proposed next action
2026-11-11 | Elkitch – Driver App | Verify Google Sheets/Drive sync and trip KM, mileage, fuel type, volume, amount, driver filter and manual sync. | Sample trip reconciled between driver app, sheet and gate records. | Medium | Use a test record and check access permissions. | Proposed next action
2026-11-12 | Elkitch – Gate Management / Gate App | Test gate-entry logs and vehicle/fuel details sync with the Driver App; review timestamp/time-zone and checkout behavior. | Matched sample entry/exit records with correct timestamps and vehicle details. | High | Confirm any current timezone or checkout-log issue before closure. | Proposed next action
2026-11-16 | Elkitch – Agentic AI Factory | Review pilot readiness, cost estimate and evaluation results; prepare a go/no-go summary. | One-page readiness report covering access, data quality, cost, permissions, evals and next approval. | High | Schedule after access and pipeline checks; date may shift if approvals are delayed. | Proposed next action